## Dashboard
LIKELIHOOD | Highly Likely | 5 | #REF! | #REF! | #REF! | #REF! | #REF!
| Likely | 4 | #REF! | #REF! | #REF! | #REF! | #REF!
| Possible | 3 | #REF! | #REF! | #REF! | #REF! | #REF!
| Unlikely | 2 | #REF! | #REF! | #REF! | #REF! | #REF!
| Rare | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Very Low | Low | Moderate | High | Very High
IMPACT
Active Risks - by Risk Levels
Shows the number of risks according to each Level
Active Risks
Total risks under active management
17
Mitigated Risks
Percentage of risks that are mitigated so far
5%
RISK DASHBOARD
Risk Heatmap
Heatmap showing all Active Risks
Risk above tolerance
% of risks that exceed the tolerance level
85%
Accepted Risks
Percentage of risks that have been accepted
10%
Overdue Risks
Number of risks that are overdue
12
Risk Categories
Shows the count of active risks under each Category
New risks reported
Risks reported per month
Average Risk Score
Shows the average of all risks, over a 12 month period

## Heatmap (hidden)
LIKELIHOOD | Highly Likely | 5 | 10 | 15 | 20 | 25
| Likely | 4 | 8 | 12 | 16 | 20
| Possible | 3 | 6 | 9 | 12 | 15
| Unlikely | 2 | 4 | 6 | 8 | 10
| Rare | 1 | 2 | 3 | 4 | 5
|  | Very Low | Low | Moderate | High | Very High
IMPACT

## Gantt chart
| Gantt start | 2024-01-01
| Interval (months) | 1
Risks | Start | Due | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
1 - Risk 1 | 2024-04-09 | 2024-11-23 | bar: 2024-05-01 to 2024-11-01
2 - Risk 2 | 2024-02-03 | 2024-10-12 | bar: 2024-03-01 to 2024-10-01
3 - Risk 3 | 2024-02-04 | 2024-11-02 | bar: 2024-03-01 to 2024-11-01
4 - Risk 4 | 2024-02-17 | 2024-08-11 | bar: 2024-03-01 to 2024-08-01
RISK GANTT CHART

## Risk Register
RISK TREATMENT PLAN
| Risk Identification |  |  |  | Risk Analysis |  |  |  | Risk Evaluation |  | Risk Treatment Plan | [5 empty] | Risk Response |  | Residual Risk | [5 empty] | Tracking |  | Calculations for Pivots
Risk ID | Asset | Risk Description | Threat | Vulnerability | Likelihood | Imapct | Risk score | Risk Level | Risk Owner | Existing measures and controls | Inherent Risk Level | Inherent Risk Rating | Risk Response Strategy | New measures and controls | Residual Impact Level | Residual Impact Rating | Residual Likelihood Level | Residual Likelihood Rating | Residual Risk Level | Residual Risk Rating | Risk Status | Status comments | Risk Due Date | Risk Close Date | Overdue? | Next Review Date
1 | Website (Web Application) | Hackers Changing website content, breaking donation forms or stealing or destroying sensitive data | Session Hijacking by Hackers (XSS), SQL injection (hackers Manipulate input fields to insert malicious commands) | outdated software, weak passwords (default administrative password), Exposed session token, insecure login pages (HTTP) | 3 | 4 | 12 | High | IT Admin | Strong Admin passwords All Data in Transit is encrypted (Full HTTPS Coverage) | High | 12 | Mitigate | Require MFA for all useraccounts and adminstrative panels, Deploy a Web Application Firewall ( Block attacks like SQL injection and cross site scripting), parameterised queries completely blocking sql injection | Very Low | 2 | Rare | 1 | Low | 2 | Open |  | 2026-07-30
2 | Third -Party server/ Hosting provider | Data Loss due to provider outages or system failure, website downtime | Data Center disasters or host level cyberattacks | Total reliance on Third party without independent backups | 2 | 4 | 8 | Medium | IT Admin | Using a well known reliable Hosting provider | Medium | 8 | Accept | None - Continous Monitoring | [6 empty] | open |  | 2026-07-30
3 | Beneficiary Data | Unauthorised access to Sensitive Data, Life threatening breaches, Legal penalties, Reputational damage, | Cyber attack, Inside Misuse of personal information, | Inadequate access control, Data Stored in unsecured files, Inadequate staff awareness/training, Lack of data retention policy | 3 | 5 | 15 | Very High | Data Protection Officer/ Safeguarding Lead | stored digitally in Cloud account, Restricted access ( stritctly to frontline staff) | Very High | 15 | Mitigate | Encrypt sensitive data, conduct regualar access reviews Provide data protection training Implement strigent access control | Moderate | 3 | Unlikely | 2 | Medium | 6 | Open |  | 2026-07-30
4 | Volunteer records | Volunteer personal details being stolen or lost, Data breach | Hackers targeting personal information, social enginerring, Ransomeware attacks, | Weak access controls, Unable to spot phishing emails(Lack of awareness), Unencrypted personal device, Poor offboarding procedure, Shared Staff Accounts | 3 | 3 | 9 | Medium | Volunteer cordinator | Stored in a spreadsheet on the office Laptop | Medium | 9 | Accept | None - Monitoring | Very Low | 1 | Unlikely | 2 | Low | 2 | Closed |  | 2026-07-30
5 | Donor Information | unauthorised access to donor personal information, Reputational damage, regulatory fines, data breach | Cybercriminals targeting data, Third part breaches, Phishing & social engineering | weak access controls, poor data handling, misconfigoured clod storage, unpatched software | 3 | 4 | 12 | High | Fundraising director | Secure storage of Donor's Information, Access control | High | 12 | Mitigate | Implement Role Based Access Control (RBAC) encrypt donor data, and provide GDPR awareness to Staffs, Third Party due deligence, clear data privacy clauses in vendor contracts, MFA. Firewalls and regular patching | Moderate | 3 | Unlikely | 2 | Medium | 6 | Open |  | 2026-07-30
6 | Safeguarding Records | Safeguarding information is accessed by unauthorised persons, data leak Reputational damage, Legal penality from (ICO), | Insider threats, Nosy staff or external hackers encrypting safeguarding serevers and also threaten to leak child protection details on dark web | Keeping physical files unlocked and digital files in shared folders, week access control, lack of clear data sharing policy. | 4 | 5 | 20 | Very High | Safeguarding lead | Physical Files kept in a file cabinet Digital Files kept in a shared folder | Very HIgh | 20 | Mitigate | Restricted folder permission, External sharing disabled, mandatory MFA, , Apply principle of least priviledge | Severe | 5 | Rare | 1 | Medium | 5 | Open |  | 2026-07-30
7 | Online Donation Platform | Donation platform is compromised or unavailable, funds are diverted | cyber attack,system failure, cyber criminals hijacking payment links | Weak security controls, Third party dependence, outdated website plugins | 3 | 5 | 15 | Very High | Fianance Director | Third Party processor is used so the charity never handles raw card data, session timeout after 15mins | Very High | 15 | Mitigate | Apply strict MFA, Run automated vulnerability scan and always apply patch were necessary | Moderate | 3 | Rare | 1 | Low | 3 | Open |  | 2026-07-30
8 | Email System/ Microsoft 365/Google Workspace | Email accounts are compromised, accounts lockout loss of data within cloud systems, | Spear Phishing, credential theft, account take over (BEC) or data exfiltration by hackers | Weak Passwords, Lack of user awareness, Not enabling two step verification (MFA) Missing domain authentication records (SPF, DKIM, DMARC) | 4 | 5 | 20 | Very High | IT Admin | Basic spam and phishing filter is enabled by the charity's provider | Very High | 20 | Mitigate | Stop domain spoofing, Restrict App consent, Bloack Hidden forwaring rules. | Moderate | 3 | Rare | 1 | Low | 3 | Open |  | 2026-07-30
9 | Staff laptops/Mobile devices | Loss of device or malware infection through email phishing could expose sensitive data, | Theft, Malware, Malware & Ransomware | Lack of encryption and endpoint protection, No BitLocker/FileVault , Outdare operating system and aoo, lack of MDM, unregulated BYOD | 3 | 5 | 15 | Very High | IT Admin | Staff uses their own security lock Antivirus installed in Laptops/Mobile devices | Vwer High | 15 | Mitigate | Apply Patch Management sutomated weeklly, Hard frive should be encrypted via bit locker | moderate | 3 | Unlikely | 2 | Medium | 6 | Open |  | 2026-08-20
10 | Financial Records | Financial records are alreted, lost or misused | Fraud, Human error, Cyber attack | Lack or regualar accounting backups, weak financial controls, insecure spreadsheet ledger storage. Single Authorization payment workflow. | 3 | 4 | 12 | High | Financial Director | Files saved on the Finance Director's Laptop | High | 12 | Mitigate | segregation of duties, Implement Access control and Authentication | Moderate | 3 | Rare | 1 | Low | 3 | Open |  | 2026-09-20
11 | Social Media Account | Social media accounts are compromised Risk of reputational damage through offensive hacker post | Hackers hijacking account to post scam messages, brand Impersonation by cybercriminals. Attackers takeover the acount and lock the admin out | Lack of MFA, reusing weak passwords across channels or sharing login info, unrestricted access rights. | 3 | 4 | 12 | High | IT Admin | Turn on notifications for unrecognised login attempts | High | 12 | Mitigate | Monitor Account activity, Use strong unique password and use MFA, establish a clear policy on what staff can post. Access right withdrawn during offboarding | Low | 2 | Rare | 1 | Low | 2 | Open |  | 2026-08-20
12 | Policices and Procedures | Operational downtime, Policy fail compliance requirements, Risk of regulatory penalty | Accidental file deletion or hardrive failure, Regulatory changes, poor review process | No backup in the cloud. Lack of scheduled policy review, outdated policy, lack of policy approval from Board of Trustees, Jargon or unclear written policies, policy missing version control | 2 | 4 | 8 | Medium | Operations Manager | Staff and relevant parties have physical copies on their desktops | Medium | 8 | Accept | Board of trustees signs off policies annually , policies should be updated against new threats, communicate policy to team and organise short training for staffs , | low | 2 | Rare | 1 | low | 2 | Closed |  | 2026-10-20
13 | Backup Data | Data loss due to backup failure, Backup data is unavailable during an incident | Ransomware, Physical theft/disaster, insider threat, | Lack of testing and backup monitoring, physical theft or diasaster, insufficient Backup retention policy, Lack of Encryption on backup files | 4 | 5 | 20 | Very High | IT Admin | Backups run automatically to an attached hard drive | very high | 20 | Mitigate | Automated backup validation and mandatory quartely test, Backup admin Login locked with separate MFA, Backup should be encrypted both at rest and in transit | Severe | 5 | Rare | 1 | Medium | 5 | Open |  | 2026-09-20
14 | Office Building | Risk of physical destruction of building, lost of paper work and Disruption to charity operations, unauthorised access | Physical theft, fire outbreak, flooding, Taligating | Limited physical security controls, Lack of smoke alarms, lack of visiot tracking logs, clear desk policy failure | 3 | 4 | 12 | high | Operations Manager | Normal door locks on the front entrance | High | 12 | Mitigate | implement Electronic badge entry and strict visitor policies, fire proof filing cabinets for paper records, automated offsite cloud backups, enforce clear desk and clear screen policy | Moderate | 3 | Unlikely | 2 | Medium | 6 | Open |  | 2026-10-20
15
16
17
RISK REGISTER

## Tasks
[8 empty] | Related Risks |  | Calculations for Pivots
Task ID | Created Date | Task Title | Task Description | Assignee | Status | Due Date | Comments | Risk ID | Risk Title | Overdue? | Due Month | Due Year | Risk-ID-Title-Combo | Residual-I-L-Combo | Mitigated? | Current Risk Level
Task Tracker for Risks

## Rating factors
Impact Level | Impact Rating | Description
-- Select Impact -- | --- Error ---
Very Low | 1 | Negligible adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation.
Low | 2 | Limited adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation. A limited adverse effect means that, for example, the threat event might: (i) cause a degradation in mission capability to an extent and duration that the organization is able to perform its primary functions, but the effectiveness of the functions is noticeably reduced; (ii) result in minor damage to organizational assets; (iii) result in minor financial loss; or (iv) result in minor harm to individuals.
Moderate | 3 | Serious adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation. A serious adverse effect means that, for example, the threat event might: (i) cause a significant degradation in mission capability to an extent and duration that the organization is able to perform its primary functions, but the effectiveness of the functions is significantly reduced; (ii) result in significant damage to organizational assets; (iii) result in significant financial loss; or (iv) result in significant harm to individuals that does not involve loss of life or serious life-threatening injuries.
High | 4 | Severe or catastrophic adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation. A severe or catastrophic adverse effect means that, for example, the threat event might: (i) cause a severe degradation in or loss of mission capability to an extent and duration that the organization is not able to perform one or more of its primary functions; (ii) result in major damage to organizational assets; (iii) result in major financial loss; or (iv) result in severe or catastrophic harm to individuals involving loss of life or serious life-threatening injuries.
Severe | 5 | Multiple severe or catastrophic adverse effects on organizational operations, organizational assets, individuals, other organizations, or the Nation.
Likelihood Level | Likelihood Rating | Description
-- Select Likelihood -- | --- Error ---
Rare | 1 | These risks have a low probability of occurring, as the name suggests.
Unlikely | 2 | Unlikely risks have an 11-40 percent chance of occurring, and it’s wise to monitor them.
Possible | 3 | Possible risks have a 41-60 percent chance of occurring and may happen about half the time, needing attention.
Likely | 4 | Likely risks have a 61-90 percent chance of occurring. They require regular attention and a consistent strategy.
Certain | 5 | Risks in this category are almost certain to occur, with a likelihood of 91 percent or more.
Risk Rating | Risk Level | Action
1 | Low | Automatically acceptable no management action needed
2 | Low
3 | Low
4 | Low
5 | Medium | Acceptable if only the cost of fixing is too high (cost of mitigation is greater than impact) or Risk score/level is within the Organisation's risk appetite.Risk acceptance with sign off
6 | Medium
7 | Medium
8 | Medium
9 | Medium
10 | High | Too dangerous to accepted. The risk should be mitigated
11 | High
12 | High
13 | High
14 | High
15 | Very High | Unacceptable, It should be actively mitigated
16 | Very High
17 | Very High
18 | Very High
19 | Very High
20 | Very High
21 | Very High
22 | Very High
23 | Very High
24 | Very High
25 | Very High

## Dropdowns
Risk Response Type
-- Select Risk Response --
Accept
Avoid
Mitigate
Transfer
Risk Status
-- Select Risk Status --
Open
In Progress
Closed
Task Status
-- Select Task Status --
Not Started
In Progress
On Hold
Closed
Risk Category | Category description
-- Select Risk Category --
Data breach | Risks of unauthorized access, exposure, or theft of sensitive data, including personal information and IP.
Ransomware | Risks of infection from malicious software, including ransomware attacks that can lead to data encryption and financial demands.
Insider Threats | Risks posed by employees or contractors with access to systems, whether from malicious intent, negligence, or accidental data loss.
Supply Chain | Risks associated with the security practices of third-party service providers, vendors, and supply chain partners.
System Vulnerabilities | Risks related to weaknesses in various systems, network infrastructure, software, or hardware that could be exploited by attackers.
Social Engineering | Risks from deception techniques aimed at manipulating individuals into divulging sensitive information or granting unauthorized access.
Identity and Access | Risks of unauthorized access due to poor identity and access management practices, including compromised credentials.
Non-compliance | Risks of non-compliance with cybersecurity laws, standards, or regulations that could lead to fines, sanctions, or reputational damage.
Operational Disruption | Risks related to disruptions in business operations due to cyber incidents, such as DDoS attacks or IT system failures.
Response and Recovery | Risks of inadequate or delayed response to cyber incidents, worsening impact, extending recovery times, and increasing costs.
Department
-- Select Department --
Compliance
Customer Service
Finance
Human Resources (HR)
Information Technology (IT)
Internal Audit
Legal
Marketing
Operations
Procurement
Product Development
Research and Development (R&D)
Risk Management
Sales

## Asset Inventory
ASSET INVENTORY
Asset ID | Asset Name | Asset Owner | Asset classification
A001 | Website | IT Manager | Public
A002 | Donor Information | Fundraising Manager | Confidential
A003 | Volunteer records | Volunteer Coordinator | Confidential
A004 | Beneficiary data | Safeguard Lead | Confidential
A005 | Safe guarding records | Safeguard lead | Confidential
A006 | Social media accounts | IT Manager | Public
A007 | Financial records | Finance Manager | Confidential
A008 | Email system | IT Manager | Internal
A009 | Microsoft 365/ Google workspace | IT Manager | Internal
A010 | Staff laptops | IT Manager | Internal
A011 | Mobile Phones | IT Manager | Internal
A012 | Office Building | Facilities Manager | Internal
A013 | Backup data | IT Manager | Confidential
A014 | Online Donation Platform | Fundraising Manager | Confidential
A015 | Policies and Procedures | Board of Trustees | Internal
A016 | Third party Server/Hosting Provider | IT Manager | Confidential